## Alec
Alec Tasks
Task | Status | Priority | Estimated Effort | Remainder
Controller Input: Left Analog Stick | Completed | High
Controller Input: Right Analog Stick | Completed | High
Controller Input: Left Pad | Completed | High
Controller Input: Triggers | Completed | High
Controller Input: ABXY | Completed | High
Define the scope of the Prototype | Completed | High
Movement with Analog Stick | Completed | High
Movement has a friction coefficient associated with it | Completed | High
Create a PERT chart (or equivalent) for the Alpha | Completed | Stretch
Implement character stats: health, remaining_shield, shield_penalty_time, max_movement_speed | Complete | High
Implement levelup mechanic, allowing the player to increase their health by calling the level_up() function | Complete | High
Implement Inventory (backend): the 4 weapon slots, shield slot, and functions to swap items | Complete | High
Implement the storage locker(backend): 1 weapon slot, 1 shield slot, and functions to swap items | Obsolete | High
Implement Shield Mechanic (temporary animation): Toggle shield on button held, damage reduces shield, shield slowly ticks down when held, shield recharges when not used, shield breaks impose penalty | Complete | High
Upload Mockup of Inventory UI: Displays the 4 weapons, shield slot (no tooltips) | Obsolete | High
Upload Mockup of HUD. Display health, shield, shield penalty (if active), held items. | Complete | High
Implement Inventory UI mockup. Slots should be populated with the actual item held in the "backend" part of this. May make use of some temporary art | Obsolete | High
Implement HUD mockup (no minimap, no tooltips). Values displayed should be accurate, although some temporary art will be used | Complete | High
Upload mockup of storage locker UI. Should store 1 weapon and 1 shield item, along with some way to remove/swap an item. | Obsolete | Stretch
Implement the storage locker UI. 1 Weapon/1 Shield and some way to swap | Obsolete | Stretch
Implement a generic format for text tooltips that can take a string and display it. | Complete | High | 2 | 0
Implement weapon tooltips for items on the HUD, displayed upon mousing over the item | Complete | High | 0.5 | 0
Implement shield tooltips for items on the HUD, displayed upon mousing over the item | Complete | High | 0.5 | 0
Implement a tooltip showing health and shield remaining when mousing over the healthbar | Complete | High | 0.5 | 0
Create Milestone Chart, highlighting each sprint's goal until beta | Complete | High | 4 | 0
Modify the textbox to be able to handle small images, so that we can display graphics like a little "A" button during the tutorial text. | Complete | High | 2 | 0
Modify the textbox and tooltips to handle coloured text | Complete | High | 2 | 0
Implement mockup of the main menu (extremely limited audio/graphical settings) | Complete | High | 4 | 0
Modify tooltips to display item quality (legendary, epic, rare, uncommon, common ) | Complete | High | 3 | 0
Restyle UI to make it look more sleek and sci-fi | Complete | Stretch | 4 | 0
Remap keyboard controls | Assigned | Complete | 1.5 | 0
Tutorial - where to go? | Assigned | Complete | 0 | 0
Add audio for menu, guns, interactables. | Assigned | Complete | 3 | 0
Add health packs to UI | Assigned | Complete | 1 | 0
Add some ambient sounds to dungeon 1 | Assigned | Complete | 1 | 0
Add credits to main menu | Assigned | Complete | 0.1 | 0
Modify credits: blue background, white text, center text, scale text up a bit | Assigned | Complete | 1 | 0
Credit sound authors in credits section. | Assigned | Complete | 0.2 | 0
Implement BGM | Assigned | Complete | 0.5 | 0
Improved Movement | Assigned | Complete | 0 | 0
Add lore books | Complete | ALPHA | 2 | 0
Prepare debrief presentation | Complete | ALPHA | 4 | 0
Set up bug tracking using Github's issues feature. Then, add all known bugs to the tracker (include all bugs from alpha day) | Complete | High
Revise the milestone chart based on feature changes going into the final and beta. Also include revised weekly sprint goals. | Complete | High
360 Review | Complete | High
Create a new PERT chart for the beta, similar to the one for alpha. | Complete | High
Add the part of the death animation where the background fades to black | Completed | High | 2 | 0
Bugfix the tutorial death to include the fade to black and remove the "dungeon killed you" text | Completed | High | 3 | 0
Make the UI healthbar flash when taking damage | Completed | High | 1 | 0
Make the UI shieldbar flash when taking damage. | Completed | High | 1 | 0
Bugfix chests so that closed chests are no longer interactable, overriding the priority of nearby guns. | Completed | High | 1 | 0
Move the arrows on tooltips to the item on the ground | Completed | High | 1 | 0
Make the player's shield recharge rapidly after clearing a room | Completed | High | 1 | 0
Bugfix chests so that they no longer spawn items inside solid walls | Completed | High | 3 | 0
Add a tooltip to components | Complete | Stretch | 1 | 0
Make books disappear after they're picked up | Complete | Stretch | 1 | 0
Make health bar flash at low HP | Complete | Stretch | 1 | 0
Make enemy laser sounds not stack | Complete | Stretch | 1 | 0
Implement New Grunt Sounds | Complete | High | 1 | 0
Implement New Dog Sounds | Complete | High | 1 | 0
Implement New Captain Sounds | Complete | High | 1 | 0
Implement New Brute Sounds | Complete | High | 1 | 0
Implement New Azar Sounds | Complete | High | 1 | 0
Implement New Dym Sounds | Complete | High | 1 | 0
Implement New Thwander Sounds | Complete | High | 1 | 0
Implement New Shuude Sounds | Complete | High | 1 | 0
Implement New Heart Sounds | Complete | High | 1 | 0
Move the player spawn point to the right of the library in the hub | Complete | High | 2 | 0
Move the world teleporters down and arrange them in a straight line in the hub | Complete | High | 1 | 0
Simple Movie Teaser Trailer | Complete | High | 2 | 0
Finish implementing the new tutorial (3 rooms + Lyra dialog) | Waiting on room 3 art | High | 8 | 0
Add a new UI for lore books, showing locked and unlocked books. | Complete | Stretch | 7 | 0
Storyboards Draft | Complete | Stretch | 5 | 0
Fix shield recharge rate to no longer be a % of max shield, scaling with the +max shield health. | Complete | High | 1 | 0
Fix difficulty settings to globally increase player damage taken, not enemy damage. Also, they probably aren't affecting bosses? | Complete | High | 1 | 0
Audio doesn't stop when pausing | Complete | High | 1 | 0
Lighting and windows in hub+tutorial | Complete | High | 1 | 0
Sound: Ambient sounds for the basic enemies | Assigned | High | 3 | 0
Sound: Laser door open/close | Assigned | High | 1 | 0
Sound: Weapon drop | Assigned | High | 1 | 0
Sound: Workbench interacted | Assigned | High | 1 | 0
Sound: Spike activated | Assigned | High | 1 | 0
Sound: Book interact | Assigned | High | 1 | 0
Sound: Cube pickup | Assigned | High | 1 | 0
Sound: Computer boot up for library | Assigned | High | 1 | 0
Sound: Boss 4 Music | Assigned | High | 2 | 0
Sound: Final Boss Music | Assigned | High | 2 | 0
Sound: Boss Taking Damage (1 per boss = 5 sounds) | Assigned | High | 1 | 0
Sound: Boss Phase 2 activation (1 per boss = 5 sounds) | Assigned | High | 1 | 0
Sound/Design: Depth events for bosses (1 per boss = 4 events) | Assigned | High | 2 | 2
Prevent the player from dashing/moving/shooting when windows like the lore book one are open | Complete | High | 1 | 0
Fix text overflow on weapon tooltips (Marvelous Auto Rifle) | Bug
Trailer

## Dominick
Dominick Tasks
Task | Status | Priority | Estimated Effort | Remainder
Complete Code Style Guide - TSD | Completed | High
Version Control Guide - TSD | Completed | High
File Format Guide - TSD | Completed | High
Workflow Guide - TSD | Completed | High
Game Maker Asset Guide - TSD | Completed | High
Slack Communication Guide - TSD | Completed | High
Prototype Dungeon Map Generator | Completed | High
Prototype Room Position To Dungeon Position Mapping | Completed | High
Prototype Room Transitions | Completed | Stretch
Prototype Room Snapshoting | Completed | Stretch
Prototype Dungeon Map Display | Completed | Stretch
Implement Isomorphic Camera | Completed | High
Implement Scrolling Credits | Completed | High
Implement (Empty) Save Format | Completed | High
Implement projectiles (enemy and player). Projectiles are entities with velocity and no AI. Collisions are handled in another task. | Completed | High
Implement swords attacks, using placeholder art | Completed | High
Implement dropped items. The player can click on these dropped items to interact with them. (Pickup may be blocked until the next sprint due to the inventory system - tooltips not necessary) | Completed | High
Collision geometry for anything solid: player, walls, entities, projectiles. | Completed | High
Room sizing tool that generates the code required to register rooms in the dungeon generator | Completed | High
Isomorphic Depthing so that objects are properly ordered based on their Y position | Completed | High
Merge all dungeon rooms on a floor into a single room | Completed | Stretch
Add target platform information to TDD | Completed | High | 0.05 | 0
Implement dungeon 1 - enemy 1 - based on design doc. Use placeholder art. | Completed | High | 2 | 0
Implement HUD Minimap in the space provided near the healthbar/shield bar | Completed | High | 2 | 0
Implement Tech to play sound effects when an action occurs. (Use placeholder soundtrack, add key toggle to turn on/off until sound settings) | Completed | High | 1 | 0
Implement Tech to play background music in a dungeon/the hub. Allow the music to loop. (Use placeholder soundtrack, add key toggle to turn on/off until sound settings) | Completed | High | 1 | 0
Implement walls and doors around dungeon room stubs | Completed | High | 3 | 0
Implement the ability to interact with certain entities on the game world. Only entities we specify as interactable can be interacted with | Completed | High | 1 | 0
Implement multiple levels in dungeons. | Completed | Stretch | 1 | 0
Ensure Dungeons always have a consistent entrance | Completed | Stretch | 0.5 | 0
Implement monster spawners that can spawn either monsters or traps in a room | Completed | High | 1 | 0
Implement tech for traps (as a part of the actual world) | Completed | High | 0.5 | 0
Implement tech for Invisible walls | Completed | High | 0.1 | 0
Add a script to detect player presence in a room | Completed | High | 0.5 | 0
Add the ability to overwrite a (normal) room with another (moment) room during the dungeon generation. | Completed | High | 2 | 0
Add "bleeding numbers" to the game world | Completed | Stretch | 0.1 | 0
Add an ingame pause menu | Completed | Stretch | 0.5 | 0
Add ability to generate fixed sized dungeons | Completed | High | 1 | 0
Implement Room Gating | Completed | Stretch
Bug: Main menu new game does not start a new game | Completed | Stretch
Add a shader, to be used for the pause menu, that renders the world in grayscale. | Completed | Stretch | 0.1 | 0
Bugfix: Gun position | Completed | Stretch
Bugfix: Save format (inventory) | Completed | Stretch | 0.5 | 0
Update Dungeon Generator To allow Shaped rooms | Completed | Stretch | 2 | 0
Implement clone script then kill self | Completed | Stretch | 1 | 0
Implement Transition Screen When Loading New Levels | Complete | Stretch
Implement both parts of the tutorial. | Complete | High
If not implemented in the tutorial, some brief explanation of your mission, etc (story element) | Complete | High
Add in the final boss door opening when you complete the cube | Complete | High
Add in the boss of dungeon 1 (even if it's a pickle monster). Have it drop a cube piece and grant a health powerup. | Complete | High
Add in the final boss (even if it's a pickle monster). Killing it wins the game + plays credits. | Complete | High
Audio settings do something. | Completed | High
Add healthpack item to the world that can be picked up | Completed | High
Add a weapon creation script, that can be used to create weapons with proper stats | Completed | High | 1
Add a shield creation script, that can be used to create shields with proper stats | Completed | High | 1
Implement ammo mechanic | Completed | High
Ensure Dungeons always spawn a boss room at the end | Completed | High
Death drops held item | Completed | High
Invincibility frames on damage taken | Completed | Low
Enemy drops show tooltips (same as the tooltips for the UI) if you're able to pick them up. | Completed | Medium
Reskin dungeon 1, enemies | Complete | ALPHA | 2 | 2
Make the camera feel right by modifying factors such as positioning and shaking | Completed | High
Issue #73: Opening a door and walking can cause a crash | Completed | High
Add Controller Support | Completed | High
Add dog enemy | Completed | High
Align tiles to isometric tile view when generating rooms/levels | Completed | High
Move gun out from the player slightly and move back the pivot point slightly | Completed | High
Create 7 stubs with placeholder tiles. | Completed | High
360 Course Review | Completed | High
360 Review | Completed | High
Scale enemy difficulty with depth | Completed | Stretch
Make source YYC Compatible, if this is possible. | Completed | Stretch
Issue #74: Font missing some characters | Completed | Stretch
Implement IK for player and maybe enemy arms | Completed | Stretch
Add chromatic abberation on damage taken | Completed | Stretch
Add player damage flash (white -> black -> normal) | Completed
Implement player death screen | Completed
Create 7 Stubs | Completed
Captain AI | Completed
Brute AI | Completed
Boss #1 AI | Completed
Boss #2 AI | Completed
Boss #3 AI | Completed
Boss #4 AI | Completed
Final Boss AI | Completed
Plasma Shots Rotate | Completed
Teleport Room Implemented. | Completed
Make plasma shots 25% slower and leave everything else the same speed | Completed
Player can now complete the cube and progress through the dungeon fully | Completed
Bug #69: Player can get stuck in a gate | Completed | Beta
Bug #134: Boss #4 can sometimes crash | Completed | Beta
Bug #135: Fullscreen toggle (F11) crashes if the game is paused | Completed | Beta
Bug #131: Font is missing several characters. | Completed | Beta
Bug $147: Final Boss Broken | Completed
Animate grunt arms with IK | Obsolete | High
Animate captain arms with IK | Obsolete | High
Animate boss 3 arms with IK | Obsolete | High
Add dash mechanic | Completed | High
Add vsync option | Completed | High
Fix the first boss' animations | Completed | High
Encrypt save file | Completed | High
Add game versions to save file | Completed | High
Show depth on minimap | Completed | High
Show level time on minimap | Completed | High
Visually deactive teleporter during tutorial | Completed | High
Shrink Azar ~25% | Completed | High
Shrink final boss ~50% | Completed | High
Add snare trap | Completed | High
Add landmine (bomb) trap | Completed | High
Add poison trap | Completed | High
Explosive bullets implemented | Completed | High
Add muzzle flashes | Completed | High
Make grunts shoot 1 bullet | Completed | High
Make boss 3 more accurate | Completed | High
Show boss teleporters before they become active | Completed | High
Add new cursor | Completed | High
Minimap improvements (show health items and teleporters on the map - there are icons) | Completed | High
Add shield flash | Completed | High
Add boss unique guns | Completed | High | 0.1 | 0.1
Add cube progress to right side of pause menu | Completed | High | 0.1 | 0.1
Add player stats(level, HP, Shield, Shield Upgrades, Components)/image to left side of pause menu | Completed | High | 0.1 | 0.1
Fix controller support | Completed | High | 0.1 | 0.1
Add options menu to the ingame pause menu | Completed | High | 0.1 | 0.1
Add lootbeams animation (not for commons?) | Completed | High | 0.1 | 0.1
Create additive light stencils | Completed | High | 0.1 | 0.1
Boss 4: Add attack that fires a lot of bullets in a 180 degree arc | Assigned | High | 0.1 | 0.1
Increase dash distance | Completed | High | 0.1 | 0.1
Boss 3: Now attempts to launch traps at the player, and uses a trap after each shooting phase | Assigned | High | 0.1 | 0.1
Hook Attack for Boss 3 | Obselete | Stretch | 0.1 | 0.1
Make worm boss slow down | Completed | Stretch | 0.1 | 0.1
Add Boss Intro Screens | Completed | High | 1 | 1
Implement gun names bank (adlib with [adjective] [gun noun]) | Completed | High | 1 | 0
Main menu art | Completed
Planet transition art/animation thing | Completed
Skin the credits. | Completed
Fix Interact Bug | Completed
Create Intro Cutscene | Completed
Create Teleport Effects | Completed
Steam page/website

## Nick
Nick Tasks
Task | Status | Priority | Estimated Effort | Remainder
Main Character - Static Sprite | Complete | High
Enemy - Grunt Static Sprite | Complete | High
Weapon - Rifle Sprite | Complete | High
Art Style - Tile pieces | Complete | High
Art Style - Set Piece | Complete | Stretch
Art Style - Colour Pallete | Complete | High
Art Bible - Add above | Complete | High
Create storyboards for the first section of the game up until the player enters dungeon 1 | Complete | High
Art bible - suggested resolutions for inventory weapon/shield sprites, items dropped in the world, enemies, player. Guidelines/templates for animation. Suggested colour palettes for the HUB, and dungeons 1-3 based on suggested themes. More intricate details for dungeon 1 are expected. | Complete | High
Redesign character sprite using thumbnails workflow | Complete | High
Vardus - Partial Desert Tileset - make part of the tileset for the first dungeon. Includes a couple floor tiles and the wall tiles | Complete | High
Use enemy thumbnails to come up with a revised enemy #1 sprite design | Assigned | High
Vardus - Dungeon 1 Splash Art - Finished art piece showing the planets environment in a more realistic style, can be used for loading screens | Complete | High
Partial hub tileset - walls and floor. Requires at least one floor tile and a few wall tiles. (no objects) | Complete | High | 3 | 0
Enemy #2 silhouette | Complete | High | 1 | 0
Enemy #3 silhouette | Complete | High | 1 | 0
Enemy #4 silhouette | Complete | High | 1 | 0
Boss #1 silhouette | Complete | High | 1 | 0
Dungeon 1 - Enemy 1 - Static sprite | Completed | High | 3 | 0
Dungeon 1 - Enemy 3 - Static sprite | Completed | High | 3 | 0
Finish tileset for tutorial room and hub (except set pieces) | Completed | High | 4 | 0
3 Weapon Sprites | Assigned | Complete
Player damage flashing animation | Obsolete | Ignore
Muzzle Flash Animations | Assigned | Complete
360 Course Review | Assigned | Complete
Cleanup and merge the hub+desert tilesets. Includes adding bleeding to tiles. | Assigned | Complete
360 Review | Assigned | Complete
Basic Grunt Sprite (Enemy #1 by the old numbering) | Assigned | Complete
Player walk animation | Assigned | Complete
Final boss door | Complete | Critical
Refined both tilesets, addressing issues with room trims | Complete | Critical
Brute static sprite (Enemy #4 by old numbering) | Complete | Critical
Final boss static sprite (Is this already done?) | Complete | Critical
Cube fragments (hub) - shows the cube 25%, 50%, 75%, 100% done | Complete | Critical
Cube fragment sprite (dropped from bosses) | Complete | Critical
Component sprite | Complete | High
Boss 1 Animation - Attacks | Complete | High
Workbench sprite (interactable object in world) | Complete | Medium
Chest open and closed sprites | Complete | Medium
Multiple different book sprites | Assigned | Low
Boss Static Sprite #2 | Complete | High
Boss Static Sprite #3 | Complete | High
Boss Static Sprite #4 | Complete | High
Dead grass, dying rivers, "hard dirt" tiles | 75% | High
Bookshelf tiles | complete | High
Table tiles (horizontal) | complete | High
Unique gun sprites for boss #2, #3, #4, and the item granted by the final boss | complete | High
"Lootbeam" Sprites | Complete | High
Remake book sprite | complete | High
Sparkle effect for certain interactable items. | complete | High
Animate Grunt Enemy - Walk | complete | High | 1 | 1
Grunt Attack Animation | done | High | 1 | 1
Animate Dog Enemy - Walk | complete | High | 1 | 1
Animate Captain Enemy - Walk | done | High | 1 | 1
Captain Attack Animation | done | High | 1 | 1
Animate Brute Enemy - Walk | 50% | High | 1 | 1
Animate Brute Enemy - Attack | done | High | 1 | 1
Boss 3 Animation - Walk | done | High | 1 | 1
Boss 3 Animation - Drop trap | done | High | 1 | 1
Revised Rock Sprite | complete | High | 1 | 1
Trap sprites | complete | High | 1 | 1
Add light to normal and final door sprites | complete | High | 1 | 1
Borders for boss teleporters | complete | High | 1 | 1
Turret Sprite | complete | High | 1 | 1
Depth Meter | complete | High | 1 | 1
Finalized New Tileset by adding transition tiles | complete | High | 1 | 1
Player death animation | Done | High | 1 | 1
Title screen art - Probably an image of Vardus from space | complete | Stretch | 1 | 1
Make lasers skinnier | complete | Stretch | 1 | 1
Character portraits: J, Lyra, Broadcasting System, Book, a Question Mark, Azar, Dym, Thwander (size these 128x128 if possible, else try for 64x64) | done | High | 1 | 1

## Spencer
Spencer Tasks
Task | Status | Priority | Estimated Effort | Remainder
Dungeon 1 Level Design. Include walls, traps, room layouts, room connections, room escalation, enemy placment, items etc. | Complete | High
Dungeon 1 Enemy Designs I - Weak Monster. Include how the enemy will attack, their health proportions, their movement, their range, there strengths and abilities | Completed | High
Dungeon 1 Enemy Designs II - Strong Monster (Melee). Include how the enemy will attack, their health proportions, their movement, their range, there strengths and abilities | Completed | High
Dungeon 1 Enemy Designs III - Strong Monster (Ranged). Include how the enemy will attack, their health proportions, their movement, their range, there strengths and abilities | Completed | High
Dungeon 1 Enemy Designs IV - Brute. Include how the enemy will attack, their health proportions, their movement, their range, there strengths and abilities | Completed | High
Player Mechanics. Include how te player will move in all aspects, running jumping, walking, how they will interact with items and enemys, how the player will take damage, inventory, locker, etc. | Completed | High
Game Economy. Include the mechanics behind gun loot, gun rarity, health and shielding, how to get health back, damage and unlocking mechanics. | Complete | High
Design Doc as a collection of feature briefs. Includes dungeon 1, player mechanics, game economy, and some preliminary information on dungeons 2 and 3. | Completed | High
Dungeon 1 Boss Design. Include how the enemy will attack, their health proportions, their movement, their range, there strengths and abilities | Completed | High
Dungeon 2 Level Design. Include walls, traps, room layouts, room connections, room escalation, enemy placment, items etc. | Completed | High
Dungeon 2 Enemy Designs I - Weak Monster. Include how the enemy will attack, their health proportions, their movement, their range, there strengths and abilities | Completed | High
Dungeon 2 Enemy Designs II - Strong Monster (Melee). Include how the enemy will attack, their health proportions, their movement, their range, there strengths and abilities | Completed | High
Dungeon 2 Enemy Designs III - Strong Monster (Ranged). Include how the enemy will attack, their health proportions, their movement, their range, there strengths and abilities | Completed | High
Dungeon 2 Enemy Designs IV - Brute. Include how the enemy will attack, their health proportions, their movement, their range, there strengths and abilities | Completed | High
Feature brief detailing the non-combat tutorial. Include core mechanics to be highlighted, in what order they're highlighted, and what the player must do at every step of the tutorial. | Complete | High | 2 | 0
Feature brief detailing the combat tutorial. Similar to the non-combat tutorial: include core mechanics to be highlighted, in what order they're highlighted, and what the player must do at every step of the tutorial. | Complete | High | 2 | 0
Implement ~9 dungeon 1 rooms stubs of various sizes, using the tileset completed last sprint. Just empty rooms and maybe traps; no monsters. ~3 each of small, medium, large. | Assigned | High | 5 | 0
Implement the hub map, excluding set pieces and interactables. That is, do not implement interactables such as world teleporter, door to the final boss as part of this task | Assigned | High | 5 | 0
Dungeon 1 music | Complete | High
Hub Music | Complete | ALPHA
Boss Music | Complete | ALPHA
Final Boss Music | Complete | ALPHA
Main Menu Music | Complete | ALPHA
Credit Music | Complete | ALPHA
Fix the tutorial design, based on feedback and alpha testing. Look at, at least: Inventory system, Health Pickups, Health, Ammo Mechanic | Assigned | Complete
360 Review | Assigned | Complete
Boss #3 Design | Assigned | Complete
Boss #4 Design | Assigned | Complete
Design Action Indicators for: Weapon pickup, death, healthpack, out of ammo, reload | Assigned | Complete
Grunt Sounds: Attack, Getting Hit, Death | Completed | High | 2 | 0
Dog Sounds: Attack, Getting Hit, Death | Completed | High | 2 | 0
Captain Sounds: Attack, Getting Hit, Death | Completed | High | 2 | 0
Golem Sounds: Attack, Getting Hit, Death | Completed | High | 2 | 0
Azar Sounds: Music, Basic, Groud Slam, Rock Throw, Rock Wave, Death | Completed | High | 3 | 0
Dym Sounds: Music, Basic, Cloud Slash, Cloud Port, Grab, Summon Cloud, Death | Completed | High | 3 | 0
Thwandar Sounds: Music, Basic, Drop mine, Hook, Stasis trap, Rapid Shot, Death | Completed | High | 3 | 0
Shuude M'ell Sounds: Music, Basic, Grab, Scream Beam, Echolocate, Death | Completed | High | 3 | 0
Heart Sounds: Music, Basic, Spawn, Quad Laser, I created you, electro port, Death | Completed | High | 3 | 0
Reload sounds for weapons | Obsolete | High | 1 | 0
Depth Completed sound | Completed | High | 1 | 0
Depth Music | Completed | High | 1 | 0
Component Dropped | Completed | High | 1 | 0
Weapon Dropped | Completed | High | 1 | 0
Sound: Ambient sounds for the basic enemies | Completed | High | 3 | 0
Sound: Laser door open/close | Completed | High | 1 | 0
Sound: Weapon drop | Completed | High | 1 | 0
Sound: Workbench interacted | Completed | High | 1 | 0
Sound: Spike activated | Completed | High | 1 | 0
Sound: Book interact | Completed | High | 1 | 0
Sound: Cube pickup | Completed | High | 1 | 0
Sound: Computer boot up for library | Completed | High | 1 | 0
Sound: Boss 4 Music | Completed | High | 2 | 0
Sound: Final Boss Music | Obsolete | High | 2 | 0
Doc: Gun names bank (adlib with [adjective] [noun]) | Completed | High | 3 | 0
Sound: Boss Taking Damage (1 per boss = 5 sounds) | Completed | High | 1 | 0
Sound: Boss Phase 2 activation (1 per boss = 5 sounds) | Completed | High | 1 | 0
Doc/Play: Play the game through a couple of times, logging any missing sounds, balance issues, or bugs | Assigned | Friday | 5 | 5
Sound/Design: Depth events for bosses (1 per boss = 4 events) | Completed | High | 2 | 0
Design: Phase 2 for Bosses 2-4 | Completed | High | 2 | 0
Design: Fix Bosses | Completed | High | 2 | 0
Sound/Design: Phase cut Music For Bosses | Obsolete | High | 2 | 2